QF632 Financial Data Science — Group Project

Team Working Guide

Topic: Predicting the JKM–TTF LNG Price Spread from European Gas Fundamentals

0.  Read This First

This document is the shared playbook for our project. It locks down what we are building and why, lists the non-negotiable methodology rules the rubric grades us on, and splits the work across six members. Please read all of it before our first sync — the goal is that nobody re-litigates the topic and everyone knows exactly what they own.

One-line summary: We forecast the JKM–TTF spread (Asian minus European gas benchmark) using free European supply/demand data, with Linear Regression and PCA only, and we treat the limits of free data as part of the analysis rather than hiding them.

1.  Settings

1.1  The target we predict

- Target = the JKM–TTF spread, not the level of either price. JKM (Japan–Korea Marker) is the Asian spot LNG benchmark; TTF (Title Transfer Facility) is the European gas benchmark. Both are quoted in $/MMBtu, so the spread is unit-consistent.

- We model changes / log-returns of the spread, never raw price levels — gas prices are highly non-stationary (the 2022 spike), and the brief’s Lesson 4 explicitly says “use returns not price levels.”

- Economic logic (our “mosaic thesis”): US LNG cargoes have destination flexibility — they sail to whichever region pays more. So the JKM–TTF spread is effectively the market price of an arbitrage/routing option, and it should respond to relative supply–demand tightness between Asia and Europe.

1.2  The methodology

- Linear Regression and PCA only (plus their textbook diagnostics). The brief’s Milestone 3 grades exactly these two and nothing else; Lesson 3 stresses parsimony, interpretability, and “start simple.” We do NOT add game theory, neural nets, or other heavy models — they cost us points, not gain them.

- PCA is used the way the course’s Nike example does: to orthogonalize correlated inputs (remove multicollinearity) before/inside the regression.

1.3  The data-availability assumption (“Case A”)

We assume Case A: our signals are either free real-time, or free-but-lagged versions of data that would arrive in real time if purchased (e.g., GIE publishes a gas-day value 1–2 days later, but the value itself existed on the gas day).

- Therefore we align every feature on its event date (the gas day / load day it actually refers to) to simulate the “we bought the real-time feed” environment.

- Aligning on the event date is not look-ahead bias, because “real-time” means known as soon as it happens, not “knowing the future.” The one rule: never align on a calculation/forward value that could not have existed yet.

- We still store the publish date too (see Rule R2) so we can measure how much the lag would cost us — that becomes our “is the paid data worth buying?” argument.

2.  Why This Topic Scores Well (Rubric Map)

The project is graded on four equally weighted (25% each) criteria. Here is how our topic hits each — keep these in mind so every deliverable defends a criterion.

| Rubric criterion (25% each) | How our project earns it |
| --- | --- |
| 1. Creativity & Thesis Formulation | Original free-data angle on a real arbitrage (LNG destination flexibility); the spread is interpretable as an option value. |
| 2. Data Rigor & Preprocessing Integrity | Multi-frequency merge (daily prices / daily storage / monthly flows / daily weather), point-in-time event vs publish dates, deseasonalisation, z-score scaling. |
| 3. Methodological Competence & Diagnostics | LR with residual / VIF / Durbin-Watson checks AND PCA with scree + loadings — both diagnostic families, done transparently. |
| 4. Communication & Operational Awareness | Futures liquidity, contract roll, turnover, plus the “value of timeliness / should we buy the paid feed” business case. |

3.  Timeline (Hard Deadlines)

| Date | Milestone | What must exist |
| --- | --- | --- |
| May 30 | M1 — Feasibility Proposal | 1-page memo: Core Thesis + Data Source & Access Protocol + Proof of Ingestion (printed first 5 rows of real ingested data). |
| June 6 | M2 — Preprocessing & EDA | Time-series alignment write-up (no leakage) + scale/missing-data handling, with EDA plots. |
| June 13 | M3 — Modelling & Diagnostics | Preliminary LR and/or PCA outputs WITH diagnostic proof (residual scatter, multicollinearity, autocorrelation / scree + loadings). |
| June 16 | Final — 15-min Quant Pitch | Institutional-grade pitch (15 min + 5 min Q&A) following the 5-part structure in §6. |

Internal buffer: aim to finish each milestone 2 days early so the modelling pair always has clean inputs.

4.  Data Sources Cheat-Sheet (all free)

| Data | Source / access | Frequency | Notes |
| --- | --- | --- | --- |
| TTF gas price | Investing.com download / Barchart | Daily | European benchmark; front-month futures. Free history. |
| JKM LNG price | Barchart futures / TradingEconomics | Daily | Proxy for the Platts assessment — disclose that the official series is paid (good rigor point). |
| EU gas storage | GIE AGSI+ API (free key) | Daily | Fill levels / injections / withdrawals. Publishes D+1–2 — record event & publish dates. |
| LNG into Europe | GIE ALSI API (free key) | Daily | Terminal inventory + send-out (regasification) flow = LNG actually entering the EU grid. |
| Weather | Open-Meteo (no key) | Daily | Convert to Heating Degree Days (HDD), population-weighted over key EU demand centres. |
| US LNG exports | EIA / DOE monthly report | Monthly | Coarse, lagged. Use only as a directional control, flagged as a lower-bound proxy. |

5.  Non-Negotiable Methodology Rules

These are the things the rubric punishes hardest. Everyone follows them; the modelling pair enforces them.

- R1 — Predict the spread in changes, prove it is modellable. Before any modelling, confirm the spread is stationary / mean-reverting (ADF test) and that JKM & TTF are cointegrated. If not, we redefine the target.

- R2 — Two date columns on every series. Each row carries event_date (when it refers to) and publish_date (when it became public). Primary models run on event_date (Case A); the gap powers the timeliness-value analysis.

- R3 — No look-ahead, ever. A feature for predicting day t may only use information whose event_date ≤ t (Case A) and must be lag-shifted relative to the forward spread move we predict.

- R4 — Deseasonalise storage. Never feed raw storage level. Use “deviation from 5-year seasonal norm” or “days of cover.” Storage has a strong summer-fill / winter-draw cycle.

- R5 — Standardise scales. z-score all features (mean 0, sd 1) so bounded and unbounded variables are comparable and coefficients are interpretable.

- R6 — Treat 2022 as a regime break. Test for it (Chow test); prefer modelling the post-2022 “LNG era” rather than splicing in pre-2022 pipeline-era data. State the sample-size trade-off honestly.

- R7 — Show diagnostics, not just scores. Milestone 3 is explicit: residual scatter (homoscedasticity), multicollinearity (VIF), autocorrelation (Durbin-Watson) for LR; scree + elbow + loading interpretation for PCA.

6.  The 15-Minute Pitch Structure (target output)

Everything we build should feed one of these five slots (mandated by the brief):

- The Mosaic Thesis — the research question + the LNG-arbitrage economic logic.

- The Data Pipeline & Enrichment — ingestion hurdles, frequency matching, the mosaic.

- Model Architecture & Diagnostic Proof — LR / PCA walk-through WITH diagnostic plots.

- Operational Realities — turnover, bid-ask/roll costs, and the value-of-timeliness / buy-the-feed case.

- Q&A — defend data choices, assumptions, conclusions.

7.  Work Breakdown — Six Members

Each member owns a workstream end-to-end (data → write-up → their slide). Ownership is mapped to a milestone and a rubric criterion so nothing falls through the cracks.

| Member | Workstream | Owns milestone | Owns rubric |
| --- | --- | --- | --- |
| P1 — Lead | Thesis, economic narrative, deck assembly, Q&A prep | M1 (thesis) + Final | Criterion 1 |
| P2 | Price data + spread + stationarity/cointegration | Feeds M1 / M2 | Criterion 3 (foundation) |
| P3 | Supply data (storage, LNG send-out) + PIT infrastructure | M1 (Proof of Ingestion) | Criterion 2 |
| P4 | Demand data (HDD) + preprocessing & EDA | M2 | Criterion 2 |
| P5 | Linear Regression + diagnostics + timeliness decay | M3 (LR path) | Criterion 3 |
| P6 | PCA + diagnostics + Operational Realities | M3 (PCA path) + Final | Criterion 3 + 4 |

P1 — Team Lead & Thesis / Narrative

- Own the mosaic thesis: write the crisp research question and the LNG destination-flexibility / arbitrage logic that makes the spread predictable.

- Draft the M1 memo Section A (Core Thesis) and stitch the whole 1-page memo together from the others’ inputs.

- Run the schedule; assemble the final 15-min deck; coordinate Q&A rehearsal and likely-question prep.

- Deliverables: thesis paragraph + market-anomaly framing; assembled M1 memo; final deck; Q&A brief.

P2 — Price & Target Engineering

- Pull TTF (Investing.com/Barchart) and JKM (Barchart/TradingEconomics); align calendars and convert both to a common $/MMBtu basis.

- Construct the spread and its log-changes; document the JKM-is-a-Platts-proxy caveat.

- Critical foundation: run ADF (stationarity) and Engle–Granger cointegration on the spread. This decides whether the whole “predict the spread” framing is valid — do this before anyone builds features.

- Deliverables: clean price & spread series (with event/publish dates) + a short stationarity/cointegration report.

P3 — Supply-Side Data & Point-in-Time Infrastructure

- Register for the GIE key; pull AGSI+ (underground storage) and ALSI (LNG terminal inventory + send-out flow) via API.

- Build the shared point-in-time table: every series stamped with event_date and publish_date (implements Rules R2/R3 for the whole team).

- Produce the M1 Proof of Ingestion — the printed first 5 rows that show we cleared the access barrier.

- Deliverables: ingested supply dataset in PIT format; the dual-date join template the others build on; M1 ingestion snapshot.

P4 — Demand-Side Data & Preprocessing (M2 owner)

- Pull Open-Meteo weather for key EU demand centres; convert to population-weighted Heating Degree Days (HDD = how cold it is below the 18°C heating threshold).

- Merge all sources onto one timeline; handle frequency mismatch, deseasonalise storage (R4), z-score everything (R5), and document missing-value / anomaly handling.

- Run the EDA: correlation matrix (check our features are not redundant), seasonality plots, before/after transformation plots.

- Deliverables: the model-ready feature matrix + the full M2 write-up (alignment + scaling/missing data).

P5 — Linear Regression + Diagnostics (M3 LR owner)

- Build the LR: forward spread change ~ lagged supply tightness + HDD anomaly + LNG send-out change, on event_date alignment (Case A).

- Produce the three mandated diagnostics: residual-vs-fitted scatter (homoscedasticity), VIF (multicollinearity), Durbin-Watson / residual ACF (autocorrelation); report Newey-West robust standard errors (overlapping windows + vol clustering make plain OLS errors unreliable).

- Run the information-decay experiment: refit with the signal lagged 0 / 1 / 2 / 4 weeks (event vs publish) and plot predictive power vs lag — this is our “value of real-time data” evidence.

- Deliverables: LR results table + 3 diagnostic plots + the decay curve.

P6 — PCA + Operational Realities (M3 PCA owner + pitch part 4)

- Run PCA on the basket of correlated inputs (e.g., multiple European hub prices / several supply indicators) to extract orthogonal components; feed components into the regression to kill multicollinearity (Nike-example style).

- Produce the PCA diagnostics: scree plot with a visually justified elbow, and an interpretation of the top loading vectors as real economic themes (e.g., “European supply tightness,” “weather-driven demand”).

- Write the Operational Realities section: futures liquidity, contract roll / term structure, turnover and transaction costs, and the business case built from P5’s decay curve (“signal exists but decays inside the free-data lag → a real-time feed is worth buying”).

- Deliverables: PCA scree + loadings + interpretation; Operational Realities slides.

8.  How the Pieces Connect

Pipeline: P2 (price/spread + validity) and P3 (supply data + PIT table) and P4 (demand data + preprocessing) all feed a single merged, event-date-aligned feature matrix. P5 (LR) and P6 (PCA) model it in parallel. P1 wraps the economic story around the result and assembles the pitch; P6 closes with operational realities.

Dependency order: P2’s cointegration check and P3’s PIT table are upstream of everything — if either breaks, modelling waits. So P2 and P3 sprint first; P4 merges; P5/P6 model; P1 narrates throughout.

Reminder: depth on ONE clean LR + PCA with transparent diagnostics beats a pile of shallow models. The rubric rewards rigor and honesty about limitations, not complexity.